## Tabelle1
Report Reference Nr.: | Recommended Measures: | Responsible Proponent: | Completed By Date: | Comment from Company:
2.1 Management Responsibilities | Formally appoint an IT security representative to coordinate all information security activities and issues within the company as required by the Würth PAP Chapter IT-Compliance. Ideally, and in order to avoid potential conflicts of interest, the appointed information security manager should not be the same individual as the IT Manager. | Ramón Ferrer | 2018-03-01 | he will be appointed in march
2.2 Risk Management | Define a risk assessment and risk management approach for the entire company and its branches that include all aspects of critical business operations and not just the IT infrastructure. Use the risk analysis to develop a disaster recovery plan. | Yuvenny Ramirez | 2018-04-30
2.3.1 Windows Environment | Update all software, which is “end of life” and therefore not supported with security updates anymore. Only actual software (especially operating systems) should be used due to security reasons. | Yuvenny Ramirez | 2018-04-30
2.3.2 Network Infrastructure | Establish formal processes for the setup of routing, avoiding unwanted or unnecessary routing between the network segments in use. | Yuvenny Ramirez | 2018-04-15 | switches to be aquired and cable in order to create redundancy
| Create an OSI layer 3 network plan for the overview of all network relevant devices and network segments. | Yuvenny Ramirez | 2018-04-15 | switches to be aquired and cable in order to create redundancy
| Establish a dedicated DMZ on the firewall for the outside access to the necessary parts of the Intranet. Placing a dedicated webserver for this particular purpose in the DMZ. | Yuvenny Ramirez | 2018-03-31 | Yuvenny cotizará DMZ dedicado y evaluar la opción de comprar certificado por aplicación
2.4 Data Classification | Identify all sensitive information and perform a formal data classification to protect sensitive company information. Consider, applying the “need to know” principle in all areas. | Ramón Ferrer | 2018-05-31 | hacer levantamiento con personal clave de la empresa
2.5 Creation of Guidelines | Develop guidelines for the use of e-mail, Internet, USB sticks, smartphones and notebooks, including guidelines describing how to handle sensitive company information. | Yuvenny Ramirez | 2018-05-31
| Develop guidelines for the usage of the corporate smartphones being issued to the employees (e.g. allowance of usage, pin protection etc.). | Yuvenny Ramirez | 2018-06-30
| Develop guidelines addressing the “clean desk policy” and the locking of computers while leaving the work place. | Yuvenny Ramirez | 2018-03-31
2.6 User Awareness | Perform user awareness training, addressing all current threats and vulnerabilities when utilizing Internet and e-mail and smartphones. | Yuvenny Ramirez / Ramón Ferrer | 2018-04-01
2.7 Electronic Transmission of sensitive Information | Make sure that all traffic, transporting corporate sensitive business information and data is handled via https (TLS encrypted). | Yuvenny Ramirez | 2018-03-01 | se retomará esta práctica este mes
| Make sure that sensitive Information like a list of the full names and vendor numbers is only available with appropriate authentication (at least username and password), applying the “need to know” principle. | Yuvenny Ramirez | 2017-06-01 | already corrected
| As switching from Axapta to Dynamics, make sure that the ADM´s can transfer their orders directly into the ERP system. | Yuvenny Ramirez | 2018-04-01 | this will be done using an external "mobile sales" application
2.8 Monitoring of Accesses | Employ an appropriate solution for monitoring both the server activites and network traffic. | Yuvenny Ramirez | 2018-03-01 | Yuvenny investigará y cotizará software
2.9 Backup/Data Protection | Make sure that the backup is not generated or stored at the same location where the data is processed. A solution for an offsite storage of the backup should be developed as soon as possible. The solution could e.g. be to use two external hard disks with a permanent hardware encryption. Those hard disks could be exchanged on a regular basis (according to the risk analysis) e.g. daily or weekly. One of the hard disks then should be stored offsite in a secure place e.g. a bank vault. | Yuvenny Ramirez | 2018-04-01 | hablar con la gente de Banco Popular para contratra la caja de seguridad y comprar discos duros
2.10 Compliance | Uninstall the Dropbox clients and training the users on compliance with the cloud ban. | Yuvenny Ramirez | 2018-03-31 | Mkt lo usaba pero se desinstalará
| Find a solution to substitute Dropbox. This could e.g. be an ownCloud server, hosted in a future DMZ of the company. | Yuvenny Ramirez
| Reconsider the planned solution for the web shop. As it was planned by the time of the audit, the solution would not only be “cloud based” but also include a high error rate as the data of an order would be sent via e-mail and has to be entered manually into the ERP system. Furthermore, this solution involves the danger of understocking. | Yuvenny Ramirez | 2018-05-31 | a new web shop is being developed under a new platform accessing the data information directly to AX
2.11 Physical Security | Consider the physical construction and situation of the property while doing the risk analysis. | Yuvenny Ramirez | 2018-05-31 | we will evaluate possibilities and costs in order to get our server safe
| Install a temperature- and water sensor in the server room, including an automated alarming. | Yuvenny Ramirez | 2018-05-31 | we will evaluate possibilities and costs in order to get our server safe
2.12 Business Continuity | Develop a formal disaster recovery plan, including potential down- and restoring time. | Yuvenny Ramirez Ramón Ferrer | 2018-05-31
| Make plans for having a redundancy for business critical hardware such as servers or appliances (e.g. firewall, routers, switches etc.). At least, having business critical systems included in an according disaster recovery planning. | Yuvenny Ramirez Ramón Ferrer | 2018-05-31
2.13 User Management | Develop a process and establish the acknowledgment to a non-disclosure agreement for all employees, including trainees. | Claudia Suero | 2018-04-30
2.14 Handling of Data Media | Establish processes for the handling of data media, assuring used storage devices are destroyed in a proper way. Also taking in account, that modern “smart multifunctional printers” are equipped with hard drives to store either scans or print jobs. Those data often remains on the devices, if they are exchanged (while leased) or decommissioned. | Yuvenny Ramirez | already done
3.1.1 User Permission Authorization and Account Configuration (ERP sys-tem) | Establish a detailed access rights concept, following the “need to know” principle as requested within the PAP | Yuvenny Ramirez